## Sheet1
Week 1
| MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY | Start Date
| 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-12 | 2026-09-13
| Finalize problem statement: predicting startup fail / acquired / IPO using funding velocity & timng instead of raw totals raised. | Create GitHub repo; set up JupyterHub environment; do a first light look at the Big Startup Success/Fail (Crunchbase) dataset on Kaggle to confirm needed fields exist (funding dates, rounds, status, category). |  | Team review of business case draft; incorporate feedback; draft discussion post responding to Week 1 prompt. | Finalize and post discussion. Finalize written report to PDF. Push repo structure + report to GitHub. Submit all artifacts. | Buffer / catch-up if behind. | Off / light review only.
Week 2
| MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
| 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20
| Ingest the Big Startup Success/Fail dataset into pandas; inspect columns, dtypes, shape, and general dataset stats. | Define target variable(s): primary status class (operating / acquired / closed / IPO) and secondary duration target for a later survival-analysis view (event = closed, censored = still operating). | Define predictor plan: funding-velocity features (time to first round, time between rounds, acceleration/deceleration of round size or frequency), industry category, location, total funding as a control variable. | Run exploratory descriptive stats in the notebook (missingness, distributions of funding gaps); start drafting the required document. | Finalize the 10-page doc (target/predictor rationale + dataset exploration + stats) to PDF. Push notebook + PDF to GitHub. Post discussion. Submit. | Buffer / catch-up if behind. | Off / light review only.
Week 3
| MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
| 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27
| Decide split strategy,, use a time-based split to avoid leakage, since this is a time-to-event problem. Implement train/validation/test split. | EDA on the training set only: distributions of velocity features, class balance across fail/acquired/IPO, and duration distribution for the survival piece. | Bivariate EDA: velocity/timing features vs. outcome status; correlations; breakdowns by industry category. | Identify data issues: missing funding dates, zero/negative time gaps, and how to define censoring correctly for 'operating' companies. | Summarize EDA findings and the issues list in the notebook. Push notebook + code output to GitHub. Post discussion. Submit. | Buffer / catch-up if behind. | Off / light review only.
Week 4
| MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
| 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04
| Handle missing values in funding dates/rounds; decide impute vs. drop, fit only on training data. | Treat outliers in funding-velocity metrics (e.g., cap extreme time gaps); log-transform skewed money/time variables. | Encode categorical variables (industry category, region) . Fit encoders on train only. | Apply the same fitted transformations to validation and test sets; verify no leakage occurred. | Document every preprocessing decision and rationale in the notebook. Push cleaned datasets/code to GitHub. Post discussion. Submit. | Buffer / catch-up if behind. | Off / light review only.
Week 5
| MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
| 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11
| Engineer velocity features: days to first round, average days between rounds, funding acceleration (round-over-round $ growth vs. time gap), rounds per year. | Engineer at least one more combined feature from 2+ raw fields (e.g., $ raised per month of operation, a 'momentum score'). | Assess need for augmentation (likely not needed on real data note and justify) and dimensionality reduction (group rare industries, check correlated features). | Finalize modeling-ready train/val/test feature sets; double-check no post-outcome leakage (e.g., don't use funding totals only available after the outcome date). | Document feature-engineering choices. Push notebook + final feature sets to GitHub. Post discussion. Submit. | Buffer / catch-up if behind. | Off / light review only.
Week 6
| MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
| 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-18
| Choose baseline classifier for the fail/acquired/IPO target (e.g., multinomial logistic regression); confirm scope for the survival piece as an extension in a later week. | Variation 1: default hyperparameters . Train and evaluate on train/val. | Variation 2: change one hyperparameter (e.g., regularization strength) train and evaluate. | Variation 3: change another hyperparameter (e.g., class weighting, since fail/acquired/IPO is likely imbalanced) train and evaluate. | Compare the 3 variations on validation metrics, select the winner, and write up the comparison. Push notebook. Post discussion. Submit. | Buffer / catch-up if behind. | Off / light review only.
Week 7
| MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
| 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-24 | 2026-10-25
| Choose a more complex model than Week 6 (e.g., Random Forest or Gradient Boosting) for the same classification target. | Variation 1: default hyperparameters. Train and evaluate. | Variation 2: tune one hyperparameter (e.g., tree depth / n_estimators) train and evaluate. | Variation 3: tune another hyperparameter (e.g., learning rate) train and evaluate; compare against Week 6's winner. | Select the winning variation and document the comparison vs. the simpler model. Push notebook. Post discussion. Submit. | Buffer / catch-up if behind. | Off / light review only.
Week 8
| MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
| 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31 | 2026-11-01
| Choose your most complex approach (e.g., XGBoost/LightGBM, or introduce a formal survival model such as Cox Proportional Hazards / Random Survival Forest for the time-to-failure angle). | Variation 1: default/baseline configuration. Train and evaluate. | Variation 2: tune one hyperparameter. train and evaluate. | Variation 3: tune another hyperparameter. Train and evaluate; compare against Weeks 6–7 winners. | Select the winner and document the full comparison. Push notebook. Post discussion. Submit. | Buffer / catch-up if behind. | Off / light review only.
Week 9
| MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
| 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-07 | 2026-11-08
| Compile all 9 model variations (3 each from Weeks 6–8) with their validation metrics into one comparison table. | Re-verify metric consistency across all models (same val set, same metric definitions); check train-vs-val gaps for overfitting. | Select the overall best-performing model based on validation metrics. | Run the selected model on the test set; compute test metrics; sanity-check test vs. validation performance. | Write up the selection rationale and test performance. Push notebook. Post discussion. Submit. | Buffer / catch-up if behind. | Off / light review only.
Week 10
| MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
| 2026-11-09 | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-13 | 2026-11-14 | 2026-11-15
| Error analysis on the Week 9 best model: examine misclassified/high-error cases (e.g., specific industries, very short-lived startups) for patterns. | Design and apply data improvement #1 (e.g., refine how censored 'operating' companies are handled, or add a velocity feature suggested by the error analysis). | Design and apply data improvements #2 and #3 (e.g., re-treat outliers, add a derived feature, address class imbalance). | Refit/retrain the Week 9 model architecture on the updated data; compute new validation metrics; compare vs. the Week 9 best. | Write the 10-page report (3 improvements, error analysis, comparison, final model choice, train/val/test error comparison and insights). Push. Post discussion. Submit. | Buffer / catch-up if behind. | Off / light review only.
Week 11
| MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
| 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-19 | 2026-11-20 | 2026-11-21 | 2026-11-22
| Compute feature importance (top 5–10 predictors) for the final model. | Select 5 random predictions; generate local explanations (e.g., SHAP) showing which features drove each and what would flip the prediction. | Identify any protected/sensitive categories or proxies in the dataset (e.g., region as a geography-based proxy) and whether they're used in the model. | Analyze bias: check for prediction disparities across categories and correlations with protected proxies; draft bias-removal strategies; note other stakeholder risks. | Write the full report (importance, explanations, protected categories, bias analysis, removal strategies, other risks). Push. Post discussion. Submit. | Buffer / catch-up if behind (or optional extra-credit bias-removal retraining). | Off / light review only.
Week 12
| MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
| 2026-11-30 | 2026-12-01 | 2026-12-02 | 2026-12-03 | 2026-12-04 | 2026-12-05 | 2026-12-06
| Serialize the final model as a pickle file; document environment dependencies (OS, Python version, package versions via requirements.txt). | Decide batch vs. real-time inference deployment and justify the choice for this use case. | Define monitoring metrics (model, business, data) and set green/yellow/red thresholds for each. | Define risk mitigation strategies per flag level, retraining cadence and rationale, and discuss data/concept drift risk specific to shifting startup-funding trends. | Finalize the monitoring plan write-up. Push pickle file + requirements + docs to GitHub. Post discussion. Submit. | Buffer / catch-up if behind. | Off / light review only.
Week 13
| MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
| 2026-12-07 | 2026-12-08 | 2026-12-09 | 2026-12-10 | 2026-12-11 | 2026-12-12 | 2026-12-13
| Audit all prior weeks' notebooks; consolidate into one clean final notebook, removing exploration clutter. | Consolidate all written reports into one cohesive final report | Clean up the GitHub repo structure (README, folder organization, remove unused files). | Full run-through: execute the final notebook end-to-end error-free, capture code output, proofread the final report. | Final submission: push final notebook, code output, GitHub repo, and final report. Post discussion. Submit. | Buffer / catch-up if behind. | Off / final review only.